## Dashboard (hidden)
|  | Payment Summary | [9 empty] | 2026-07-29
EXECUTIVE DASHBOARD |  | R06-HW2C05 · SHURA WEST HOTEL 02 · FIRST FIX | [9 empty] | REF: IPA 28 · COMMERCIAL TEAM FFC
I. | Contract & Progress
ORIGINAL CONTRACT |  |  |  |  | REVISED CONTRACT |  | +7.06% vs ORIGINAL | TOTAL APPROVED WORK DONE |  | 95.36% | BALANCE TO COMPLETE |  |  | 4.644%
217501556.12 |  |  |  |  | 232860904.0022 |  |  | 222047056.4204 |  |  | 10813847.5818
SAR |  |  |  |  | SAR · UPLIFT vs ORIGINAL |  |  | SAR · GROSS CLAIMED |  |  | SAR · GROSS
II. | Work & Payment Progress | [6 empty] | III. | Variation Orders
STATUS |  |  |  | % | GROSS (SAR) | NET (SAR) |  | STATUS |  |  | COUNT |  | AMOUNT (SAR)
Total Work Done |  |  |  | 95.36% | 222047056.4204 | 165651426.8974 |  | Total Submitted VO |  |  | 74 |  | 25035631.6194
Received |  |  |  | 93.97% | 218808603.3643 | 165651426.8974 |  | Pending with FFC |  |  | 9 |  | 0
Approved via ACONEX |  |  |  | 1.391% | 3238453.0561 | 0 |  | Pending with RSG |  |  | 22 |  | 2991535.5681
Submitted in ACONEX |  |  |  | 0% | 0 | 0 |  | Pending with RSG/FFC |  |  | 4 |  | 6684748.165
Under Review |  |  |  | 1.158% | 2696379.5978 | 0 |  | Approved & Awaiting DVO |  |  | 18 |  | -23074.7487
Balance to Complete |  |  |  | 4.644% | 10813847.5818 |  |  | DVO RR Issued |  |  | 8 |  | -362299.9724
IV. | Advance Payment | [6 empty] | V. | Retention
TOTAL ADVANCE |  |  | 32.09% |  |  |  |  | TOTAL RETENTION |  | 5.0% rate
65250466.83 | [7 empty] | 11643045.2001
SAR | [7 empty] | SAR
DEDUCTED |  |  | % |  |  |  |  | DEDUCTED |  | %
65250466.8026 |  |  | 100% |  |  |  |  | 11102352.8013 |  | 95.36%
BALANCE |  |  | % |  |  |  |  | BALANCE |  | %
0.030561 |  |  | 4.684e-08% |  |  |  |  | 540692.3988 |  | 4.644%
|  | Executive Dashboard · Internal use only | [9 empty] | REF: IPA 28 · COMMERCIAL TEAM FFC · ALL VALUES IN SAR

## Payment Summary (hidden)
Chart Data (hidden)
Commercial Payment Summary |  |  |  |  | 2026-07-29 |  | Work Progress | Label | Value
COMMERCIAL | R06-HW2C05 · SHURA WEST HOTEL 02 · FIRST FIX |  |  |  | REF: IPA 28 · COMMERCIAL TEAM FFC |  | Completed | Completed | 0.95356
[7 empty] | Remaining | Remaining | 4.644%
I. | Contract Overview |  |  |  | IV. | Advance Payment | Advance | Deducted | 1
[8 empty] | Balance | 4.684e-08%
| ORIGINAL CONTRACT VALUE | REVISED CONTRACT VALUE | VARIANCE |  | TOTAL ADVANCE
| 217501556.1159 | 232860904.0022 | 7.062% |  | 65250466.8332 | 32.09% | Retention | Deducted | 0.95356
| SAR | SAR | UPLIFT vs ORIGINAL |  | SAR |  |  | Balance | 0.046439
II. | Work & Payment Progress |  |  |  | DEDUCTED | % | VO Status
[5 empty] | 65250466.8026 | 100% |  | Pending FFC | #REF!
| TOTAL CLAIMED (GROSS) |  | BALANCE (GROSS) |  |  |  |  | Pending RSG | #REF!
| 222047056.4204 |  | 10813847.5818 |  | BALANCE | % |  | Pending RSG/FFC | #REF!
| 95.4% of revised contract complete |  | 4.6% remaining |  | 3.056% | 4.684e-08% |  | Approved/Awaiting DVO | #REF!
[8 empty] | DVO RR Issued | #REF!
[5 empty] | V. | Retention
| STATUS | % COMPLETE | GROSS (SAR) | NET (SAR)
| Total Work Done | 95.36% | 222047056.4204 | 165651426.8974 | TOTAL RETENTION
| Received | 93.97% | 218808603.3643 | 165651426.8974 | 11643045.2001 | 5%
| Approved via ACONEX | 1.391% | 3238453.0561 | 0 | SAR
| Submitted in ACONEX | 0% | 0 | 0
| Under Review | 1.158% | 2696379.5978 | 0 | DEDUCTED | %
| Balance to Complete | 4.644% | 10813847.5818 | 11895232.34 | 11102352.8013 | 95.36%
III. | Variation Orders |  |  |  | BALANCE | %
[5 empty] | 540692.3988 | 4.644%
| TO BE ADDED IN CONTRACT |  | TOTAL SUBMITTED VO VALUE
| -385374.7211 |  | 25035631.6194
| APPROVED + DVO ISSUED · SAR |  | #REF!
| STATUS | COUNT | AMOUNT (SAR)
| Pending with FFC | 9 | 0
| Pending with RSG | 22 | 2991535.5681
| Pending with RSG/FFC | 4 | 6684748.165
| Approved & Awaiting DVO | 18 | -23074.7487
| DVO RR Issued | 8 | -362299.9724
| Total Submitted VO | 74 | 25035631.6194
VANGUARD | Commercial Summary · Internal use only |  |  |  | REF: IPA 28 · COMMERCIAL TEAM FFC · ALL VALUES IN SAR

## Payment Register
PAYMENT REGISTER-HW2C05
|  |  |  | -4545500.3045 |  |  | `
PROJECT DETAILS |  | Summary of IPA's (without VAT) |  |  |  | SUMMARY OF ADVANCE PAYMENT RECOVERY IPA
Project: | R06-HW2C05-5020 | Original Contract Value | 217501556.1159 |  |  | Advance Payment | 65250466.8332 | 32.09%
Contractor: | First Fix | Revised Contract Value | 232860904.0022 |  |  | Deducted till Date | 65250466.8026 | 100%
Contract Date: | 2023-09-20 |  |  |  |  | Balance | 0.030561 | 4.684e-08% | [9 empty] | .
|  | Under Review | 2696379.5978 | 1.158%
|  | Submitted on ACONEX | 0 | 0% |  | SUMMARY OF RETENTION IPA
|  | Approved via Acconex | 3238453.0561 | 1.391% |  | Total Retention | 11643045.2001 | 5%
|  | Received | 218808603.3643 | 93.97% |  | Deducted till Date | 11102352.8013 | 95.36%
[6 empty] | Balance | 540692.3988 | 4.644%
|  | Total Work Done | 222047056.4204 | 95.36%
|  | Balance Work Done | 10813847.5818 | 4.644%
No. | Claim for Month / Invoice |  | Gross Certified (Work executed) Amount | Advance Payment Recovery | Back Charge | Less Retention (10%) | VAT Recovery for Advance Payment | VAT 15% | Net Payment Certified | Payment Recieved From Client | Balance Due | Submitted Date (FFC to TRSDC 1) | Tax invoice sumbitted | Due Date | Payment Status | Status | Payment Collected Date | Remarks
[18 empty] | FFC Live Action | RSG Live Action
AP01 | Adv Payment Invoice |  | 43500311.2232 |  |  |  |  | 6525046.6835 | 43500311.2232 | 43500311.2232 |  | 2023-11-23 | 2023-04-12 |  | Paid | Received |  | Transaction Received | Transaction Placed |  | Received | Transaction Received | Transaction Placed
AP02 | Adv Payment Invoice 2 |  | 21750155.61 |  |  |  |  | 3262523.3415 | 21750155.61 | 21750155.61 |  | 2024-11-20 | 2024-11-22 |  | Paid | Received |  | Transaction Received | Transaction Placed
IPA 1 | Sept 20th 2023 – Dec 25th 2023 |  | 2571831.8036 | -514366.3607 |  | -257183.1804 | -77154.9541 | 385774.7705 | 2108902.079 | 2108902.079 |  | 2023-12-14 | 2024-01-22 |  | Paid | Received |  | Transaction Received | Transaction Placed | 2571831.8036 | Approved via Acconex | Submitted Tax Invoice via Acconex Waiting For the Transaction | To place the payment | `
IPA 2 | Dec 25th 2023 – Jan 25th 2024 |  | 1727779.4778 | -345555.8956 |  | -172777.9478 | -51833.3843 | 259166.9217 | 1416779.1718 | 1416779.1718 |  | 2024-01-30 | 2024-03-26 |  | Paid | Received | 15/04/2024 | Transaction Received | Transaction Placed | 4299611.2815 | Submitted on ACONEX | Submitted Via acconex Waiting For payment Certificate | To send the Payment Certifcate
IPA 3 | Jan 25th 2024 – Feb 25th 2024 |  | 1363441.8898 | -272688.378 |  | -136344.189 | -40903.2567 | 204516.2835 | 1118022.3496 | 1118022.3496 |  | 2024-04-22 | 2024-12-04 |  | Paid | Received | 23/04/2024 | Transaction Received | Transaction Placed | 5663053.1712 | Under Review | Sent officially via mail/ Waiting for the Redsea assesment to Submit officially on Acconex | Under Assesment
IPA 4 | Feb 25th 2024 – Mar 25th 2024 |  | 963176.5 | -192635.3 |  | -96317.65 | -28895.295 | 144476.475 | 789804.73 | 789804.73 |  | 2024-05-15 | 2024-05-13 |  | Paid | Received | 2024-10-06 | Transaction Received | Transaction Placed | 6626229.6712
IPA 5 | Mar 25th 2024 – Apr 25th 2024 |  | 6730484.9425 | -1346096.9885 |  | -673048.4943 | -201914.5483 | 1009572.7414 | 5518997.6529 | 5518997.6529 |  | 2024-05-28 | 2024-05-28 |  | Paid | Received | 14/06/2024 | Transaction Received | Transaction Placed | 13356714.6138
IPA 6 | Apr 25th 2024 – May 25th 2024 |  | 3008114.0912 | -601622.8182 |  | -300811.4091 | -90243.4227 | 451217.1137 | 2466653.5548 | 2466653.5548 |  | 2024-04-29 | 2024-06-27 |  | Paid | Received | 17/07/2024 | Transaction Received | Transaction Placed | 16364828.7049
IPA 7 | May 25th 2024 – Jun 25th 2024 |  | 3972034.6787 | -794406.9357 |  | -397203.4679 | -119161.0404 | 595805.2018 | 3257068.4365 | 3257068.4365 |  | 2024-06-26 | 2024-07-28 |  | Paid | Received | 13/08/2024 | Transaction Received | Transaction Placed | 20336863.3836
IPA 8 | Jun 25th 2024 – Jul 25th 2024 |  | 5556560.4115 | -1111312.0823 |  | -555656.0412 | -166696.8123 | 833484.0617 | 4556379.5375 | 4556379.5375 |  | 2024-08-19 | 2024-07-05 |  | Paid | Received |  | Transaction Received | Transaction Placed | 25893423.7952
IPA 9 | Jul 25th 2024 – Aug 25th 2024 |  | 6512584.83 | -1302516.966 |  | -651258.483 | -195377.5449 | 976887.7245 | 5340319.5606 | 5340319.5606 |  | 2024-08-31 | 2024-10-06 |  | Paid | Received | 2024-10-23 | Transaction Received | Transaction Placed | 32406008.6252
IPA 10 | Aug 25th 2024 – Sep 25th 2024 |  | 5212335 | -1042467 |  | -521233.5 | -156370.05 | 781850.25 | 4274114.7 | 4274114.7 |  | 2024-10-02 | 2024-10-21 |  | Paid | Received |  | Transaction Received | Transaction Placed | 37618343.6252
IPA 11 | Sep 25th 2024 – Oct 25th 2024 |  | 11178597.35 | -3587211.8896 |  | -1117859.735 | -538081.7834 | 1676789.6025 | 7612233.5444 | 7612233.5444 |  | 2024-11-23 | 2024-12-13 |  | Paid | Received |  | Transaction Received | Transaction Placed | 48796940.9752
IPA 12 | Oct 25th 2024 – Nov 25th 2024 |  | 5338593.8516 | -1713154.767 |  | -533859.3852 | -256973.215 | 800789.0777 | 3635395.5621 | 3635395.5621 |  | 2024-12-08 | 2024-12-29 |  | Paid | Received |  | Transaction Received | Transaction Placed | 54135534.8267
IPA 13 | Nov 25th 2024 – Dec 25th 2024 |  | 10523911.0645 | -3377123.0606 |  | -1052391.1064 | -506568.4591 | 1578586.6597 | 7166415.098 | 7166415.098 |  | 2025-01-19 | 2025-02-02 |  | Paid | Received |  | Transaction Received | Transaction Placed | 64659445.8912
IPA 14 | Dec 25th 2024 – Jan 25th 2025 |  | 14789522.58 | -4745957.7959 |  | -1478952.258 | -711893.6694 | 2218428.387 | 10071147.2437 | 10071147.2437 |  | 2025-02-13 | 2025-03-02 |  | Paid | Received |  | Transaction Received | Transaction Placed | 79448968.4712
IPA 15 | Jan 25th 2025 – Feb 25th 2025 |  | 14091614.85 | -4521999.2054 |  | -1409161.485 | -678299.8808 | 2113742.2275 | 9595896.5063 | 9595896.5063 |  | 2025-03-18 | 2025-03-27 |  | Paid | Received |  | Transaction Received | Transaction Placed | 93540583.3212
IPA 16 | Feb 25th 2025 – Mar 25th 2025 |  | 5147125.92 | -1651712.7077 |  | -514712.592 | -247756.9062 | 772068.888 | 3505012.6021 | 3505012.6021 |  | 2025-04-23 | 2025-05-07 |  | Paid | Received |  | Transaction Received | Transaction Placed | 98687709.2412
IPA 17 | Mar 25th 2025 – Apr 25th 2025 |  | 14619843.8 | -4691507.8754 |  | -1461984.38 | -703726.1813 | 2192976.57 | 9955601.9333 | 9955601.9333 |  | 2025-05-13 | 2025-05-24 |  | Paid | Received |  | Transaction Received | Transaction Placed | 113307553.0412
IPA 18 | Apr 25th 2025 – May 25th 2025 |  | 13904093.66 | -4461823.6555 |  | -1390409.366 | -669273.5483 | 2085614.049 | 9468201.1392 | 9468201.1392 |  | 2025-06-18 | 2025-06-28 |  | Paid | Received |  | Transaction Received | Transaction Placed | 127211646.7012
IPA 19 | May 25th 2025 – Jun 25th 2025 |  | 9497761.36 | -3047831.6204 |  | -949776.136 | -457174.7431 | 1424664.204 | 6467643.0645 | 6467643.0645 |  | 2025-06-16 | 2025-07-29 |  | Paid | Received |  | Transaction Received | Transaction Placed | 136709408.0612
IPA 20 | Jun 25th 2025 – Jul 25th 2025 |  | 6813139.26 | -2186336.3885 |  | -681313.926 | -327950.4583 | 1021970.889 | 4639509.3762 | 4639509.3762 |  | 2025-09-04 | 2025-09-16 |  | Paid | Received |  | Transaction Received | Transaction Placed | 143522547.3212
IPA 21 | Jul 25th 2025 – Aug 25th 2025 |  | 5324464.1154 | -1708620.5346 |  | 6909904.18 | -256293.0802 | 798669.6173 | 11068124.2979 | 11068124.2979 |  | 2025-09-15 | 2025-10-16 |  | Paid | Received |  | Transaction Received | Transaction Placed | 148847011.4366
IPA 22 | Aug 25th 2025 – Sep 25th 2025 |  | 6418102.3521 | -2059569.0448 |  | -320905.1176 | -308935.3567 | 962715.3528 | 4691408.1858 | 4691408.1858 |  | 2025-10-19 | 2025-11-02 | 2025-11-23 | Paid | Received |  | Transaction Received | Transaction Placed | 155265113.7887
IPA 23 | Sep 25th 2025 – Oct 25th 2025 |  | 18005054.06 | -5777821.8479 |  | -900252.703 | -866673.2772 | 2700758.109 | 13161064.341 | 13161064.341 |  | 2025-11-11 | 2025-11-27 |  | Paid | Received |  | Transaction Received | Transaction Placed | 173270167.8487
IPA 24 | Oct 25th 2025 – Nov 25th 2025 |  | 9837424.545 | -3156829.5365 |  | -491871.2272 | -473524.4305 | 1475613.6817 | 7190813.0325 | 7190813.0325 |  | 2025-12-10 | 2025-12-24 |  | Paid | Received |  | Transaction Received | Transaction Placed | 183107592.3937
IPA 25 | Nov 25th 2025 – Dec 25th 2025 |  | 10126810.41 | -3249693.4606 |  | -506340.5205 | -487454.0191 | 1519021.5615 | 7402343.9713 | 7402343.9713 |  | 2025-12-31 | 2026-01-29 |  | Paid | Received |  | Transaction Received | Transaction Placed | 193234402.8037
IPA 26 | Dec 25th 2025 – Jan 25th 2026 |  | 12479962.68 | -4004820.024 |  | -623998.134 | -600723.0036 | 1871994.402 | 9122415.9204 | 9122415.9204 |  | 2025-12-31 | 2026-02-23 |  | Paid | Received |  | Transaction Received | Transaction Placed | 205714365.4837
IPA 27 | Jan 25th 2026 – Feb 25th 2026 |  | 8942936.2206 | -2869788.2332 |  | -447146.811 | -430468.235 | 1341440.4331 | 6536973.3745 | 6536973.3745 |  | 2026-03-13 | 2026-04-12 |  | Paid | Received |  | Transaction Received | Transaction Placed | 214657301.7043
IPA 28 | Feb 25th 2026 – Mar 25th 2026 |  | 4151301.66 | -914996.43 |  | -207565.083 | -137249.4645 | 622695.249 | 3514185.9315 | 3514185.9315 |  |  |  |  | Paid | Received |  | Transaction Received | Transaction Placed | 218808603.3643
IPA 29 | Mar 25th 2026 – Apr 25th 2026 |  | 2513487.3961 |  | -1054256.25 | -125674.3698 | 0 | 218884.6719 | 1552441.4482 |  |  | 2026-06-13 |  |  | Tax Invoice sent on 23rd june 26 | Approved via Acconex |  | Submitted Tax Invoice via Acconex Waiting For the Transaction | To place the payment | 221322090.7604
IPA 30 | Apr 25th 2026 – May 25th 2026 |  | 724965.66 |  |  | -36248.283 | 0 | 108744.849 | 797462.226 | [5 empty] | Tax Invoice sent on 12th July 26 | Approved via Acconex |  | Submitted Tax Invoice via Acconex Waiting For the Transaction | To place the payment | 222047056.4204
IPA 30 | May 25th 2026 – June 25th 2026 |  | 2696379.5978 |  |  | -134818.9799 | 0 | 404456.9397 | 2966017.5575 | [5 empty] | Submitted 09th July | Under Review |  | Sent officially via mail/ Waiting for the Redsea assesment to Submit officially on Acconex | Under Assesment | 224743436.0182
GRAND TOTAL |  |  | 222047056.4204 | -65250466.8026 | -1054256.25 | -11102352.8013 | -9787570.0204 | 33148920.0256 | 168001330.5716 | 197135161.5004 | 0
The Red Sea Development Company
|  |  | 59438240.8125 | -14196127.7148 |  | 2211569.4331 | -2129419.1572 | 8915736.1219 | 54239999.4954
[5 empty] | 148847011.44 | -14352254.73
[5 empty] | 143522547.3246 | -7176127.365
| Advance Payment Recovery |  | -65250466.8026 | 216722592.305 | 14352254.7325 | -10285718.2545 |  |  | 233251797.4048 |  | ` |  | 2025-12-18
| Less Retention (10%) |  | -1054256.25 |  | 7176127.3662 |  |  |  | 244354150.2061
| VAT Recovery for Advance Payment |  | -11102352.8013 |  | 143522547.32 | 14352254.732 |  |  | 210816516.8243
| VAT 15% |  | -9787570.0204 |  | 8755464.296 |  |  |  | 1552441.4482
|  |  | 33148920.0256 |  |  | 10813847.5818
221758551.2009
232953297.363
[7 empty] | 0 | 4347866.16
Formulas:
Payment Status = IF(ISBLANK([Tax invoice sumbitted]),"",IF([Status]="Received","Paid",IF((TODAY()-[Tax invoice sumbitted])<21,"Due","Over Due")&" by "&TEXT((TODAY()-[Tax invoice sumbitted])-21,0)&" Days"))
Payment Status = IF(ISBLANK([Tax invoice sumbitted]),"",IF([Status]="Received","Paid",IF((TODAY()-[Tax invoice sumbitted])<21,"Due","Over Due")&" For "&TEXT((TODAY()-[Tax invoice sumbitted])-21,0)&" Days"))
Due Date = [Tax invoice sumbitted]+21

## VO LOG (2)
2026-07-29
[11 empty] | Revised Contract |  | 232860904.0022
REVISED CONTRACT VALUE
-519455.4632
231437159.38
231956614.8432
| S.No | VO Number | VO Date In Accinex | DVO Reference | Subject | Submission | Submission Type (RFP/VAR/Gen CORR) | Submission ref# | Response Email Ref | Assesment | Cost Proposal Value | RSG Assesment | To Summary | Status | VOR | DVO Ref | R Remarks | RSG Remarks | Raw Link | Submission Link | Status |  | Done by
| 1 | VO-02 | 2024-07-29 | DVO-CM-0002 | ETS Room Standby Equipment Removal | 2024-08-06 | VO | FFC06HW2-GENCORR-000182 | FFC06HW2-GENCORR-000182 |  |  |  | -436711.9079 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0002 | R06-HW2C05-TRS-DVO-CM-0002 | Closed Out | Closed / Agreed | Open in Aconex | View Submission |  |  | finished
| 2 | VO-01 | 2024-05-12 | DVO-CM-0001 | Change in Generator from Biofuel to Standard Tier 1 Diesel | 2024-06-09 | VO | TRS06HW2-GENCORR-000846 | TRS06HW2-GENCORR-000846 |  |  |  | -1050000 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0001 | R06-HW2C05-TRS-DVO-CM-0001 | Closed Out | Closed / Agreed | Open in Aconex | View Submission | DVO Issued |  | finished
| 3 | VO-05 | 2024-05-21 | DVO-CM-0005 | Issued for Construction (IFC N1) Documents Buildings | 2024-09-07 | VO | FFC06HW2-GENCORR-000187 | FFC06HW2-GENCORR-000190 |  |  |  | 1100693.07 | DVO Issued | R06-HW2C05-TRS-DVO-CM-0005 | R06-HW2C05-TRS-DVO-CM-0005 | Closed Out | Closed / Agreed | Open in Aconex | View Submission | DVO RR Issued |  | Roomy
| 4 | VO-05 | 2024-05-21 | DVO-CM-0005 | Issued for Construction (IFC N1) Documents Infra | 2024-09-03 | VO | FFC06HW2-GENCORR-000187 | FFC06HW2-GENCORR-000187 |  |  |  | 3001607.58 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0005 | R06-HW2C05-TRS-DVO-CM-0005 | Closed Out | Closed / Agreed | Open in Aconex | View Submission | Approved , Pending DVO |  | finished
| 5 | VO-05 | 2024-05-21 | DVO-CM-0005 | Issued for Construction (IFC N1) Documents Pool | 2024-09-04 | VO | FFC06HW2-GENCORR-000187 | FFC06HW2-GENCORR-000189 |  |  |  | 558521.84 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0005 | R06-HW2C05-TRS-DVO-CM-0005 | Closed Out | Closed / Agreed | Open in Aconex | View Submission | Pending with RSG |  | finished
| 6 | VO-08 | 2024-09-11 | DVO-CM-0008 | Changing ACCU Room to Storage Room in Asset 60 (HOH) | 2024-09-17 | VO | FFC06HW2-GENCORR-000192 | FFC06HW2-GENCORR-000192 |  |  |  | 15581.88 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0008 | R06-HW2C05-TRS-DVO-CM-0008 | Closed Out | Closed / Agreed | Open in Aconex | View Submission | Pending with RSG/FFC |  | finished
| 7 | VO-07 | 2024-10-24 | DVO-CM-0007 | Relocation of CCTV cameras (6 nr) to meet operational requirements | 2025-01-04 | VO | FFC06HW2-GENCORR-000207 | FFC06HW2-GENCORR-000207 |  | -40876.88 | 0 | 0 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0007 | R06-HW2C05-TRS-DVO-CM-0007 | Closed Out | Closed / Agreed | Open in Aconex | View Submission | Pending with FFC
| 8 | VO-15 | 2024-12-24 | DVO-CM-0015 | MEP Works inside Villas & Clusters Bathrooms and associated Interfaces | 2025-02-16 | VO | FFC06HW2-GENCORR-000212 | FFC06HW2-GENCORR-000261 |  | 10699031 |  | 10699031 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0015 | R06-HW2C05-TRS-DVO-CM-0015 | Closed Out | Closed / Agreed | Open in Aconex | View Submission | Not Eligible |  | Roomy
| 9 | VO-22 | 2025-04-21 | DVO-CM-0022 | Sewage Network final Tie-in to PPP Manhole - Additional Lift Station | 2025-05-19 | VO | FFC06HW2-GENCORR-000343 | FFC06HW2-GENCORR-000368 | 2025-08-04 | 635771.67 | 519455.4632 | 519455.4632 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0022 | R06-HW2C05-TRS-DVO-CM-0022 | Closed Out | Closed / Agreed |  | View Submission |  |  | Roomy
| 10 | VO-25 | 2025-07-09 | DVO-CM-0025 | Change from 13A single switch outlet to 13A twin switched socket outlet for the Minibar Fridge on HW2 Villas and Clusters | 2025-07-15 | VO | FFC06HW2-GENCORR-000413 | FFC06HW2-GENCORR-000413 | 2025-07-20 | 19944.67 | 17343.19 | 17343.19 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0025 | R06-HW2C05-TRS-DVO-CM-0025 | Closed Out | Closed / Agreed | Open in Aconex | View Submission |  |  | Aaqil
| 11 | VO-04 | 2024-05-30 | DVO-CM-0004 | Changing Backup Strategy to Equipment Serving ICT Rooms Instruction Reference | 2025-02-04 | VO | FFC06HW2-GENCORR-000247 | FFC06HW2-GENCORR-000247 |  | -278670.94 | -747365.9816 | -504221.15 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0004 | R06-HW2C05-TRS-DVO-CM-0004 | Closed Out | Closed / Agreed |  | View Submission |  |  | Roomy
| 12 | VO-20 | 2025-07-05 | DVO-CM-0020 | Provision of Temporary Cooling to First In Place Assets | 2025-07-19 | VO | FFC06HW2-GENCORR-000415 | FFC06HW2-GENCORR-000415 | 2025-08-23 | 669692.26 | 372927.79 | 372927.79 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0020 | R06-HW2C05-TRS-DVO-CM-0020 | Closed Out | Closed / Agreed | Open in Aconex | View Submission |  |  | finished
| 13 | VO-27 | 2025-06-08 | DVO-CM-0027 | Omission of 13A twin socket outlets and Replace with combined MEP and ELV Faceplates | 2025-07-20 | VO | FFC06HW2-GENCORR-000416 | FFC06HW2-GENCORR-000416 | 2025-08-05 | 81841.95 | 46879.8006 | 46879.8 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0027 | R06-HW2C05-TRS-DVO-CM-0027 | Closed Out | Closed / Agreed | Open in Aconex | View Submission |  |  | finished
| 14 | VO-26 | 2025-06-21 | DVO-CM-0026 | Change in Bollard Lighting Fixtures luminaire ref. LA1 | 2025-06-24 | VO | FFC06HW2-GENCORR-000406 | FFC06HW2-GENCORR-000406 | 2025-07-23 | 318771.22 | -95869.6923 | -95869.6923 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0026 | R06-HW2C05-TRS-VOR-DVO-0026 | Closed Out | Closed / Agreed | Open in Aconex | View Submission |  |  | finished
| 15 | VO-12 | 2024-11-10 | DVO-CM-0012 | HW2 Family Pool Enlargement | 2025-09-30 | VO | FFC06HW2-GENCORR-000244 | FFC06HW2-GENCORR-000244 | 2025-10-06 | 1166471.1623 | 912623.79 | 912623.79 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0012 | R06-HW2C05-TRS-DVO-CM-0012_C0 | Closed Out | Closed / Agreed |  | View Submission |  |  | Chamintha
| 16 | VO-34 | 2025-12-03 | DVO-CM-0034 | Supply and Installation of (Direct-buried type) Valve for Potable Water & Irrigation System | 2025-12-14 | VO | FFC06HW2-GENCORR-000519 | FFC06HW2-GENCORR-000519 |  | 592973.09 | 271543.2358 | 271543.2358 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0034 |  | FFC agreed with RSG value; DVO to be processed |  | Open in Aconex | View Submission |  |  | Aaqil
| 17 | VO-09 | 2024-12-30 |  | Omission of FCU's Supplying Kitchen Preparation Rooms in HoH | 2025-01-06 | VO | FFC06HW2-GENCORR-000208 | FFC06HW2-GENCORR-000208 | 2025-05-10 | -3237.5866 | -3237.5866 | -3237.5866 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0009 |  |  | FFC responded dated 6-Aug-25/ RSG to check MIR for the delivered FCU prior to the VO issuance.. | Open in Aconex | View Submission
| 18 | VO-55 | 2026-02-09 |  | Creation of Informal Sand Paths for Improved Beach Access | 2/152/2026 | VO | FFC06HW2-GENCORR-000700 | FFC06HW2-GENCORR-000700 |  | 8394.87 | 5626.23 | 5626.23 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0055 |  | Documents are submitted officially on ACONEX and wating for RSG Assessment |  | Open in Aconex | View Submission
| 19 | VO-21 | 2025-08-12 |  | Main Pool Bar - Sunken Bar Drain Piping to Waste Network | 2025-08-21 | VO | FFC06HW2-GENCORR-000443 | FFC06HW2-GENCORR-000443 |  | 10039.5759 | 2914.77 | 2914.77 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0021_C0 |  | Closed Out | Closed / Agreed | Open in Aconex | View Submission | Pending with FFC RSG rejects the cost proposal and requested for a revision. The cost is deemed very excessive due to incorrect rates applied. I (e.g RMF Filter, Heat pump, etc.). |  | Aaqil
| 20 | VO-33 | 2025-09-23 |  | Supply and installation of the required missing kitchen drainage pipelines in the Kitchen Areas at Amenity & HOH buildings | 2025-10-11 | VO | FFC06HW2-GENCORR-000463 | FFC06HW2-GENCORR-000463 |  | 100533.744 | 66373.62 | 66373.62 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0033 |  | FFC accepted RSG assessment on 12-May-2026 via email |  | Open in Aconex | View Submission
| 21 | VO-45 | 2026-01-12 |  | MEP related works due to the Lifting Station Electrical Panel Relocation | 2026-02-12 | VO | FFC06HW2-GENCORR-000681 | FFC06HW2-GENCORR-000681 |  | 252445.35 | 133703.9952 | 133703.9952 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0045 |  | FFC accepted RSG assessment on 12-May-2026 via email |  | Open in Aconex | View Submission
| 67 | VO-18 | 2025-04-16 |  | Connection of Pool Overflow Drain to Sump Pit instead of Manhole | 2025-08-06 | VO | FFC06HW2-GENCORR-000440 | FFC06HW2-GENCORR-000440 |  | 194460.1 | 109935.69 | 109935.69 | DVO Issued | R06-HW2C05-TRS-VOR-CM-0018 |  | Closed Out | Awaiting FFC response | Open in Aconex | View Submission |  |  | Hizam
| 22 | VO-11 | 2025-02-05 |  | Omission of Fire Dampers Mounted on 1 Hour Fire Rated Walls | 2025-08-02 | VO | FFC06HW2-GENCORR-000250 | FFC06HW2-GENCORR-000250 |  | -123292.18 | -237846.63 | -237846.63 | DVO RR Issued | R06-HW2C05-TRS-VOR-CM-0011 |  | Closed Out | Closed / Agreed |  | View Submission |  |  | Chamintha
| 23 | VO-13 | 2025-02-10 |  | Omission of External Emergency Lights above Fire Hose Cabinet | 2025-02-15 | VO | FFC06HW2-GENCORR-000260 | FFC06HW2-GENCORR-000260 |  | -76534.47 | -209293.04 | -209293.04 | DVO RR Issued | R06-HW2C05-TRS-VOR-CM-0013 |  | DVO RR issued for 131k after they have revised the assesmnet befor they consider BOQ now the considered the drawing we checked the drawing and agreed this value as per drawing | Closed / Agreed |  | View Submission |  |  | Hizam
| 24 | VO-06 | 2024-12-26 |  | Omission of Fire Protection Inside Transformer Rooms | 2025-08-25 | VO | FFC06HW2-GENCORR-000211 | FFC06HW2-GENCORR-000445 | 2025-03-09 | -30297.49 | -50481.69 | -50481.69 | DVO RR Issued | R06-HW2C05-TRS-VOR-CM-0006 |  | Closed Out | Closed / Agreed |  | View Submission |  |  | Hizam
| 25 | VO-19 | 2025-04-09 |  | Additional Fire Suppression system in the Signature Restaurant | 2025-06-19 | VO | FFC06HW2-GENCORR-000405 | FFC06HW2-GENCORR-000405 | 2025-07-20 | 45143.47 | 7557.19 | 7557.19 | DVO RR Issued | R06-HW2C05-TRS-VOR-CM-0019_C0 |  | Closed Out | Closed / Agreed | Open in Aconex | View Submission
| 26 | VO-39 | 2025-09-24 |  | Omit 2Nr. of Inaccessible Wall Sockets (EE-PL38) and Replace with 2Nr Floor Box having 1Nr Outlet (Electrical Provision) at Asset-14 (Children & Teen Center Bldg.) | 2025-09-25 | VO | FFC06HW2-GENCORR-000454 | FFC06HW2-GENCORR-000454 |  | 3242.53 | 1066.52 | 1066.52 | DVO RR Issued | R06-HW2C05-TRS-VOR-CM-0039 |  | Documents are submitted officially on ACONEX wating for RSG Assessment |  | Open in Aconex | View Submission |  |  | Chaminda
| 27 | VO-32 | 2025-09-23 |  | Simplification of Pools Channel Detailing in 10 nr 3 Bedroom Villa Pools | 2025-10-05 | VO | FFC06HW2-GENCORR-000456 | FFC06HW2-GENCORR-000456 |  | 18314.8 | 7667.65 | 7667.65 | DVO RR Issued | R06-HW2C05-TRS-VOR-CM-0032 |  | FFC accepted RSG assessment on 12-May-2026 via email |  | Open in Aconex | View Submission |  |  | Chamintha
| 28 | VO-28 | 2025-07-15 |  | MEP provisions related to the cocoon water feature in the reception area of the Arrival building (Asset-10). | 2025-11-16 | VO | FFC06HW2-GENCORR-000506 | FFC06HW2-GENCORR-000506 |  | 300617.6573 | 154638.39 | 154638.39 | DVO RR Issued | R06-HW2C05-TRS-VOR-CM-0028 |  |  |  | Open in Aconex | View Submission |  |  | Chamintha
| 29 | VO-16 | 2025-01-19 |  | Reduction of the primary irrigation loop along with Points of Connections (POCs) | 2025-02-03 | VO | FFC06HW2-GENCORR-000246 | FFC06HW2-GENCORR-000246 | 2025-06-22 | 81086.98 | -35608.3624 | -35608.3624 | DVO RR Issued | R06-HW2C05-TRS-VOR-CM-0016 |  | Agreed and replied | Awaiting FFC response | Open in Aconex | View Submission | FFC |  | Hassan
| 30 | VO-17 | 2025-03-11 |  | Modification to Telephone Operator Room in HOH (Asset 60) | 2025-03-19 | VO | FFC06HW2-GENCORR-000306 | FFC06HW2-GENCORR-000306 |  | 3871.55 | 3871.53 | 3871.53 | Approved , Pending DVO | R06-HW2C05-TRS-VOR-CM-0017_C0 |  | Accepted Waiting For DVO |  | Open in Aconex | View Submission |  |  | Hassan
| 31 | VO-24 | 2025-07-08 |  | Provision of electrical power connection on motorised roller shutter in the kitchen areas at HOH (Asset 60) | 2025-07-17 | VO | FFC06HW2-GENCORR-000414 | FFC06HW2-GENCORR-000414 | 2025-07-19 | 7984.66 | 1659.95 | 1659.95 | Approved , Pending DVO | R06-HW2C05-TRS-VOR-CM-0024 |  | Approved Awaiting for DVO | Awaiting FFC response | Open in Aconex | View Submission
| 32 | VO-35 | 2025-09-13 |  | SPA - Addition of Missed Small Power and Data Requirements | 15-10-20255 | VO | FFC06HW2-GENCORR-000488 | FFC06HW2-GENCORR-000488 |  | 15738.35 | 14162.59 | 14162.59 | Approved , Pending DVO | R06-HW2C05-TRS-VOR-CM-0035 |  | FFC Repied to RSG Comments |  | Open in Aconex | View Submission
| 33 | VO-43 | 2025-12-14 |  | Replacement of FOH Panic Bar Hardware on External Doors for Assets 10, 13, 22, and 23 (MEP Works | 2026-02-14 | VO | FFC06HW2-GENCORR-000698 | FFC06HW2-GENCORR-000698 |  | 8287.45 | 6694.8 | 6694.8 | Approved , Pending DVO | R06-HW2C05-TRS-VOR-CM-0043 |  | Documents are submitted officially on ACONEX and wating for RSG Assessment |  | Open in Aconex | View Submission
| 34 | VO-58 | 2026-03-11 |  | Additional Buggy Charging points (MEP Works) | 2026-03-11 | VO |  |  |  | 9603.0631 | 6089.2934 | 6089.2934 | Approved , Pending DVO | R06-HW2C05-TRS-VOR-CM-0058 |  | Closed Out | Closed / Agreed | Open in Aconex |  |  |  | Chaminda
| 35 | VO-14 | 2025-02-10 |  | Change of Fire-rated Cables Buried in the Infrastructure | 2025-02-15 | VO | FFC06HW2-GENCORR-000259 | FFC06HW2-GENCORR-000259 | 2025-06-11 | 20153.09 | -271010.81 | -180673.87 | Approved , Pending DVO | R06-HW2C05-TRS-VOR-CM-0014 |  | FFC Sent all related documents to RSG to support there Proposal waiting Reply From RSG | Awaiting FFC response | Open in Aconex | View Submission |  |  | Chamintha
| 36 | VO-57 | 2026-01-14 |  | RE: GW Light fitting to Villa terraces - Request for Quotation/Pricing | 2025-11-26 | Gen CORR | FFC06HW2-GENCORR-000704 |  |  | 270716.16 | 215100.6 | 215100.6 | Approved , Pending DVO | R06-HW2C05-TRS-VOR-CM-0057 |  | Documents are submitted via Email and wating for RSG Response | RSG: Marked-up drawings missing — please issue updated VOR with marked-up drawings included. | Open in Aconex | View Submission
| 37 | VO-49 | 2026-01-18 |  | Signature Restaurant - Additional Works associated with the Internal Planter within the All Day Dining | 2026-02-14 | VO | FFC06HW2-GENCORR-000699 | FFC06HW2-GENCORR-000699 |  | 2533.29 |  | 2533.29 | Approved , Pending DVO | R06-HW2C05-TRS-VOR-CM-0049 |  | Documents are submitted officially on ACONEX and wating for RSG Assessment on 14-Feb-2026 |  | Open in Aconex | View Submission
| 38 | VO-40 | 2025-12-24 |  | Omission of Fire extinguisher cabinet (Ref. FEC) which are built into wall and relocate the Fire Extinguiser only to the nearby joinery | 2026-01-07 | VO | FFC06HW2-GENCORR-000566 | FFC06HW2-GENCORR-000566 |  | -58940.17 | -176761 | -176761 | Approved , Pending DVO | R06-HW2C05-TRS-VOR-CM-0040 |  | Documents are submitted officially on ACONEX and wating for RSG Assessment | FFC need to review quantity | Open in Aconex | View Submission
| 39 | VO-52 | 2026-01-21 |  | A-20 Recreation Family Pool - additional washdown area including water and power provision |  | VO |  |  |  | 99190.373 | 2164.7787 | 2164.7787 | Approved , Pending DVO | R06-HW2C05-TRS-VOR-CM-0052 |  | Waiting fro Mechanical Shop Drawing From FFC Technical Team |  | Open in Acconex | View Submission
| 40 | VO-44 | 2026-01-29 |  | Omission of the sand trap louvers in Asset 67 (Minor Substation) | 2026-02-13 | VO | FFC06HW2-GENCORR-000694 | FFC06HW2-GENCORR-000694 |  | -5395.37 | -15888.9 | -15888.9 | Approved , Pending DVO | R06-HW2C05-TRS-VOR-CM-0044 |  | Documents are submitted officially on ACONEX and wating for RSG Assessment | RSG: Marked-up drawings missing — please issue updated VOR with marked-up drawings included. | Open in Aconex | View Submission |  |  | Rimash
| 41 | VO-53 | 2026-01-13 |  | Omission of Skylight Sprinklers | 2026-02-11 | VO | FFC06HW2-GENCORR-000691 | FFC06HW2-GENCORR-000691 |  | 3523.58 |  | -3956.6 | Approved , Pending DVO | R06-HW2C05-TRS-VOR-CM-0053 |  | Documents are submitted officially on ACONEX and wating for RSG Assessment on 11-Feb-2026 |  | Open in Aconex | View Submission
| 42 | VO-23 | 2025-10-29 |  | MEP works required due to relocation of Villa External Areas Showers | 2025-10-18 | VO | FFC06HW2-GENCORR-000490 | FFC06HW2-GENCORR-000491 |  | 135554.68 | 109878.25 | 109878.25 | Approved , Pending DVO | R06-HW2C05-TRS-VOR-CM-0023 |  | FFC submtted revised cost proposal via email 12-May-2026 |  | Open in Aconex | View Submission
| 43 | VO-51 | 2026-01-28 |  | MEP related work requirements due to additional HOH Kitchen Ceiling |  | VO |  |  |  | 6613.5 | 6567.42 | 6567.42 | Approved , Pending DVO | R06-HW2C05-TRS-VOR-CM-0051 |  | FFC sumitted a Revised Submission (R1) and wating for RSG Assessment |  | Open in Aconex |  |  |  | Chaminda
| 66 | VO-36 | 2025-12-03 |  | Addition of external signage control panel's and ommission of the generator annunciator panel in the Fire Command Centre |  | VO |  |  |  | -34400.1534 | -43001.6595 | -43001.6595 | Approved , Pending DVO | R06-HW2C05-TRS-VOR-CM-0036 |  | Accepted Waiting For DVO |  | Open in Aconex | View Submission
| 58 | VO-38 | 2025-12-14 |  | Addition of EV Charging Station for Hotel Asset Staff Vehicles |  | VO |  |  |  | 31104.36 | 22815.5315 | 22815.5315 | Approved , Pending DVO | R06-HW2C05-TRS-VOR-CM-0038 |  | Accepted Waiting For DVO |  | Open in Aconex
| 51 | VO-50 | 2025-12-11 |  | Implementation of Changes Following Operator and RSG Inspection – FIP Villa and Cluster (MEP Works) |  | VO |  |  |  | 143370.98 | 1851.7072 | 1851.7072 | Approved , Pending DVO | R06-HW2C05-TRS-VOR-CM-0050_C0 |  | Only 1 villa and 1 clusture required this work |  | Open in Aconex
| 53 | VO-56 | 2026-02-11 |  | Implementation of changes to the 3-Bedroom Sales Villa (MEP Works) |  | VO |  |  |  | 4531.74 | 3817.54 | 3817.54 | Approved , Pending DVO | R06-HW2C05-TRS-VOR-CM-0056 |  | Accepted Waiting For DVO |  | Open in Aconex
| 44 |  |  |  | Supplementary Conduit and Embedded Works for speciality restaurant and long bar and pool | 2024-05-27 | Gen CORR | FFC06HW2-GENCORR-000158 | FFC06HW2-GENCORR-000158 |  | 16678.63 |  | 16678.63 | Pending with RSG |  |  | Documents are submitted officially on ACONEX wating for RSG Assessment | * FFC submtted revised cost proposal via email 12-May-2026 |  | View Submission |  |  | Aaqil
| 45 |  |  |  | Kitchen Drainage Pipe Installation | 2025-02-05 | Gen CORR | FFC06HW2-GENCORR-000248 | FFC06HW2-GENCORR-000248 |  | 95183.74 |  | 95183.74 | Pending with RSG |  |  | Documents are submitted officially on ACONEX wating for RSG Assessment on 5-Feb-2025 | 0 |  | View Submission
| 46 | VO-30 | 2025-08-14 |  | MEP related works associated with the construction of the First in Place (FIP) villa pool (Asset 30-04) | 2025-10-05 | VO | FFC06HW2-GENCORR-000457 | FFC06HW2-GENCORR-000457 |  | 58330.5952 |  | 58252.9 | Pending with RSG | R06-HW2C05-TRS-VOR-CM-0030 (Rev.1) |  | Documents are submitted officially on ACONEX wating for RSG Assessment on 5-Oct-2025 | RSG: Marked-up drawings missing — please issue updated VOR with marked-up drawings included. | Open in Aconex | View Submission
| 47 | VO-31 | 2025-06-25 |  | MEP related changes to the cabanas | 2025-09-22 | VO | FFC06HW2-GENCORR-000453 | FFC06HW2-GENCORR-000453 |  | 184530.84 |  | 184530.84 | Pending with RSG | R06-HW2C05-TRS-VOR-CM-0031 |  | Documents are submitted officially on ACONEX wating for RSG Assessment on 22-Sep-2025 |  | Open in Aconex | View Submission |  |  | Hizam
2 | 48 |  |  |  | RFI-Change in Air Outlet Type and Size for Asset 60 (HOH) and Asset 61 (Utility Hub) | 2025-11-09 | RFI | FFC06HW2-GENCORR-000497 | FFC06HW2-GENCORR-000497 |  | 179556.66 |  | 179556.66 | Pending with RSG |  |  | Documents are submitted officially on ACONEX and wating for RSG Assessment on 9-Nov-2025 |  |  | View Submission
| 49 |  |  |  | Proposed changes to ICT rooms Air Outlet type and size for Asset 10 (Arrival Hub), Asset 13 (Meeting Room) and Asset 14 (Children Center) | 2026-01-07 | RFI | FFC06HW2-GENCORR-000567 | FFC06HW2-GENCORR-000567 |  | 30435.52 |  | 30435.52 | Pending with RSG |  |  | Documents are submitted officially on ACONEX and wating for RSG Assessment on 7-Jan-2026 |  |  | View Submission
| 50 | VO-46 | 2025-12-13 |  | Removal of foot wash (bib taps) on the entrance of 3 Bedroom type villas; including relocation of shower drain piping works of 3-Bedroom and 4-Bedroom |  | VO | FFC06HW2-GENCORR-000533 | FFC06HW2-GENCORR-000533 |  | 3954.51 |  | 3954.51 | Pending with RSG | R06-HW2C05-TRS-VOR-CM-0046_C0 |  | Documents are submitted officially on ACONEX and wating for RSG Assessment | RSG: Marked-up drawings missing — please issue updated VOR with marked-up drawings included. | Open in Aconex | View Submission
| 52 | VO-54 | 2026-02-09 |  | Relocation and alignment of sprinklers, smoke detector and light fittings to the Affected Areas of the FIP and Sales Villas |  | VO | [6 empty] | Pending with RSG | R06-HW2C05-TRS-VOR-CM-0054 |  | FFC Technical Team waiting clarification from RSG Technical Team talked to abdul moti he will arange combined meeting for the clarification some bilding they have mentioned TBC |  | Open in Aconex
| 54 |  |  |  | Supply of Addtional Fan for Main Pool Plant Room | 2/132/2026 | RFI | FFC06HW2-GENCORR-000695 | FFC06HW2-GENCORR-000695 |  | 10279.02 |  | 10279.02 | Pending with RSG |  |  | Documents were officially submitted on ACONEX and are awaiting RSG assessment. |  |  | View Submission
| 55 |  |  |  | Damage No 21 Chilled Water Pipe (Zone 4, Asset 31-04B) | 2025-07-22 | Gen CORR | FFC06HW2-GENCORR-000418 | FFC06HW2-GENCORR-000418 |  | 1260532.47 |  | 1260532.47 | Pending with RSG |  |  | RSG Sent a Letter on the Role of RSG to Facilitate | 0 |  | View Submission |  |  | Hassan
| 56 | VO-10 | 2025-12-14 |  | Omission of Bathroom Downlights which are to be free-issued to the MEP Contractor that were supplied by the Bathroom Pod Contractor (SBW) |  | VO |  |  |  | 0 |  | 0 | Pending with RSG | R06-HW2C05-TRS-VOR-CM-0010 |  | FFC requested that RSG reduce the cost to zero and hand over the materials. |  | Open in Aconex
| 57 | VO-61 | 2026-04-15 |  | Enhancement of Beach Cabanas | 2026-04-15 | VO |  |  |  | 151955.28 |  | 151955.28 | Pending with RSG | R06-HW2C05-TRS-VOR-CM-0061 |  |  |  | Open in Aconex
| 59 | VO-42 | 2025-12-30 |  | Type of Air Outlets Change from SLD to FBD by ID - All FOH Buildings | 2025-10-29 | VO | FFC06HW2-GENCORR-000495 | FFC06HW2-GENCORR-000495 |  | 664798.76 |  | 664798.76 | Pending with RSG | R06-HW2C05-TRS-VOR-CM-0042 |  | FFC Will Submit revised Cost Proposa 8th june | RSG: Marked-up drawings missing — please issue updated VOR with marked-up drawings included. | Open in Aconex | View Submission
| 60 | VO-48 | 2026-01-13 |  | HOH & Utility Building Ramp Light Updates, Kitchen Equipment DP Switch Addition & Cable Type Change | 2026-02-16 | VO | FFC06HW2-GENCORR-000703 | FFC06HW2-GENCORR-000703 |  | 202867.91 | 138185.75 | 202867.91 | Pending with RSG | R06-HW2C05-TRS-VOR-CM-0048 |  | FFC sumitted a Revised Submission (R1) and wating for RSG Assessment |  | Open in Aconex | View Submission |  |  | Rimash
| 61 | VO-65 | 2026-05-07 |  | Missing Items in Asset 60 (HOH) |  | VO |  |  |  | 2031.98 |  | 2031.98 | Pending with RSG | R06-HW2C05-TRS-VOR-CM-0065 |  | Cost Proposal submitted to RSG via Aconex on 15-June-2026 |  | Open in Aconex | View Submission
| 62 | VO-67 | 2026-05-13 |  | Cable containment including conduits, boxes, accessories, supports to allow P1 access panel and Door Contacts (to 3-Bed and 4-Bed Villas maid room doors) |  | VO |  |  |  | 8175.31 |  | 8175.31 | Pending with RSG | R06-HW2C05-TRS-VOR-CM-0067 |  | Cost Proposal submitted to RSG via Aconex on 15-June-2026 |  | Open in Aconex | View Submission
| 63 | VO-47 | 2026-01-13 |  | Rinse Showers Plumbing and Drainage Provisions to the HW2 main pool, family pool and fitness pool areas. |  | VO |  |  |  | 25415.75 |  | 25415.75 | Pending with RSG | R06-HW2C05-TRS-VOR-CM-0047_ |  | FFC submitted the Cost proposal on 16-June-2026 |  | Open in Aconex
| 64 | VO-66 | 2026-04-27 |  | Extension of the ductwork to connect to the newly designated location of the extract louvre including associated works to Speciality Restaurant |  | VO |  |  |  | 1730.542 |  | 1730.542 | Pending with RSG | R06-HW2C05-TRS-VOR-CM-0066 |  | Requested details from Abdul Muti. |  | Open in Aconex
| 65 | VO-63 | 2026-04-27 |  | Omission of 5A Floor boxes (ref. FB) & spike light (ref. PK) and replace with 5A switched socket outlets to the wall |  | VO |  |  |  | -17453.266 |  | -17453.266 | Pending with RSG |  |  | Prepared cost proposal; awaiting invoices for delivered FB and PK to claim from Red Sea. |  | Open in Aconex
| 71 | VO-37 | 2025-10-08 |  | Supply and Installation of cable containment for GSM Hybrid Cables |  | VO |  |  |  | 111029.0261 |  | 111029.0261 | Pending with RSG | R06-HW2C05-TRS-VOR-CM-0037 |  | FFC submitted the Cost proposal on 08-July-2026 |  | Open in Aconex
| 79 | VO-74 | 2026-07-09 |  | Relocation of Arrivals Fire Alarm Panel | [5 empty] | 624.4261 |  | 624.4261 | Pending with RSG | R06-HW2C05-TRS-VOR-CM-0074 |  | FFC submitted the Cost proposal on 29-July-2026 |  | Open in Aconex
| 80 | VO-77 | 2026-07-09 |  | HOH Offices Door Change Panic Bar to Maglock | [5 empty] | 955.56 |  | 955.56 | Pending with RSG | R06-HW2C05-TRS-VOR-CM-0077 |  | FFC submitted the Cost proposal on 29-July-2026 |  | Open in Aconex
| 68 |  |  |  | Cable Copper Price Fluctuation | 25/09/2024 | Gen CORR | FFC06HW2-GENCORR-000193 | FFC06HW2-GENCORR-000193 |  | 3010759.61 | 395793.5432 | 1505379.805 | Pending with RSG/FFC |  |  | Accepted; awaiting DVO. | Awaiting FFC response |  | View Submission
| 69 | VO-05 |  |  | HW2C05 Ligting Control System | 2025-02-18 | VO | FFC06HW2-GENCORR-000191 | FFC06HW2-RESP-000056 | 2025-04-08 | 304785.68 | 74452.02 | 304785.68 | Pending with RSG/FFC | R06-HW2C05-TRS-VOR-CM-0005 |  | Submitted to RSG; assessment and discussion ongoing to finalize with RSG. | Closed / Agreed | Open in Aconex | View Submission |  |  | Hassan
| 70 | VO-41 | 2025-12-03 |  | Request for Quotation/ Pricing - HW2 Maintenance of Temporary Utilities & Switch over to Permanent Power | 2025-11-20 | Gen CORR | FFC06HW2-GENCORR-000508 | FFC06HW2-GENCORR-000508 |  | 3423318.95 | 1546467.67 | 3423318.95 | Pending with RSG/FFC | R06-HW2C05-TRS-VOR-CM-0041 |  | Submitted to RSG; assessment and discussion ongoing to finalize with RSG. |  | Open in Aconex | View Submission |  |  | Chamintha
| 72 |  |  |  | Diesel Supply | 2025-07-23 | Gen CORR | FFC06HW2-GENCORR-000419 | FFC06HW2-GENCORR-000419 |  | 1451263.73 |  | 1451263.73 | Pending with RSG/FFC |  |  | RSG requested a detailed breakdown with proper supporting evidence.FFC Sent genarator break down | 0 |  | View Submission |  |  | Aaqil
| 73 | VO-60 | 2026-03-11 |  | Provision of fireproof sealant works associated with the GSM System Installation - External Fiber Cable works | 2026-03-11 | VO | [6 empty] | Pending with FFC | R06-HW2C05-TRS-VOR-CM-0060 |  | Quotation received; substantiation in progress. Quotation states sealant quantity as 5 pails only, so a building-by-building survey is required to identify and mark all FLS and ELV penetration points, followed by a rate breakup for each point — this will take additional time. |  | Open in Aconex
| 74 | VO-62 | 2026-03-30 |  | CCTV embedded drainage pipe survey including jetting of the pipes for any blockages | 2026-03-30 | VO | [6 empty] | Pending with FFC | R06-HW2C05-TRS-VOR-CM-0062 |  | Eng. Najeed to request PO. |  | Open in Aconex
| 75 | VO-64 | 2026-03-29 |  | Provision of Power/Lighting for External Artwork Pieces | 2026-03-29 | VO | [6 empty] | Pending with FFC | R06-HW2C05-TRS-VOR-CM-0064 |  | No shop drawing still contacted latest 22nd Jul With rami |  | Open in Aconex
| 76 | VO-69 | 2026-06-22 |  | Modifications due to Manhole clashes with Accommodation Entrance Pathways | [8 empty] | Pending with FFC | R06-HW2C05-TRS-VOR-CM-0069 |  | ‼️ NEW VOR found on Aconex (22-Jun-2026) — FFC to submit Cost Proposal Asked information from site team abdul muti he told he will give the details following up |  | Open in Aconex
| 77 | VO-68 | 2026-07-09 |  | Rerouting MEP Services Requirement (Asset 63-05) | [8 empty] | Pending with FFC | R06-HW2C05-TRS-VOR-CM-0068 |  | ‼️ NEW VOR found on Aconex (09-Jul-2026) — FFC to submit Cost Proposal |  | Open in Aconex
| 78 | VO-70 | 2026-07-06 |  | Amenities - Add Drywall, Relocate Fire Alarm Panel | [8 empty] | Pending with FFC | R06-HW2C05-TRS-VOR-CM-0070 |  | ‼️ NEW VOR found on Aconex (06-Jul-2026) — FFC to submit Cost Proposal |  | Open in Aconex
| 81 | VO-80 | 2026-07-09 |  | Relocation of MEP Outlets Due to Kitchen Coordination Issues – Assets 63-2, 63-3, 63-6 and 63-7 | [8 empty] | Pending with FFC | R06-HW2C05-TRS-VOR-CM-0080 |  | ‼️ NEW VOR found on Aconex (09-Jul-2026) — FFC to submit Cost Proposal |  | Open in Aconex
| 82 | VO-84 | 2026-07-29 |  | Arrival Speaker Removal and Making Good above Water Feature |  | VO | [6 empty] | Pending with FFC | R06-HW2C05-TRS-VOR-CM-0084 |  | ‼️ NEW VOR found on Aconex (29-Jul-2026) — FFC to submit Cost Proposal | RSG mail TRS06HW2-VAR-OR-000467 — acknowledge by 09-Aug-2026 (signature + date of signing required)
| 83 | VO-85 | 2026-07-29 |  | MBOH ICT Control Room - Replace Clean Agent with Wet Sprinkler System |  | VO | [6 empty] | Pending with FFC | R06-HW2C05-TRS-VOR-CM-0085 |  | ‼️ NEW VOR found on Aconex (29-Jul-2026) — FFC to submit Cost Proposal | RSG mail TRS06HW2-VAR-OR-000468 — acknowledge by 09-Aug-2026 (signature + date of signing required)
| 84 |  |  |  | Re: TMV location change in HW2 villas pantry | 2025-11-06 | Gen CORR | FFC06HW2-GENCORR-000496 | FFC06HW2-GENCORR-000496 |  | 152696.3 |  |  | Not Eligible |  |  | Not elligible |  |  | View Submission
[5 empty] | TOTAL APPROVED VOs Value: | [7 empty] | 25035631.6194
in asset scedule include each asset ommision and pleanum recovery for each asset
Note on N31: Mohamed Roomy Mohamed Hassan: RSG Employer Assessment accepted amount (Feb 2026). Original contractor proposal: SAR 15,738.45.
Note on O32: Mohamed Roomy Mohamed Hassan: Mohamed Roomy Mohamed Hassan: Signed and sent DVO to RSG
Note on L33: Mohamed Roomy Mohamed Hassan: UPDATED: Contractor Proposal corrected to 81,086.98
Note on M34: Mohamed Roomy Mohamed Hassan: UPDATED: RSG Assessment added (237,846.63)
Note on N34: Mohamed Roomy Mohamed Hassan: UPDATED: Final Approved Amount added
Note on O34: Mohamed Roomy Mohamed Hassan: CHANGED: Was 'Pending with RSG/FFC' → 'DVO RR Issued'
Note on O35: Mohamed Roomy Mohamed Hassan: Mohamed Roomy Mohamed Hassan: Signed and sent DVO to RSG
Note on L36: Mohamed Roomy Mohamed Hassan: UPDATED: Contractor Proposal corrected to (76,534.47)
Note on M36: Mohamed Roomy Mohamed Hassan: UPDATED: RSG Assessment added (131,416.56)
Note on N36: Mohamed Roomy Mohamed Hassan: UPDATED: Final Approved Amount added
Note on O36: Mohamed Roomy Mohamed Hassan: CHANGED: Was 'Pending with RSG/FFC' → 'DVO RR Issued'
Note on N37: Mohamed Roomy Mohamed Hassan: UPDATED: Final Approved Amount confirmed
Note on O52: Mohamed Roomy Mohamed Hassan: Mohamed Roomy Mohamed Hassan: Signed and sent DVO to RSG
Note on O53: Mohamed Roomy Mohamed Hassan: Mohamed Roomy Mohamed Hassan: Signed and sent DVO to RSG
Note on N60: Mohamed Roomy Mohamed Hassan: UPDATED: Final Approved Amount = 7,557.19 (DVO Issued)
Note on O60: Mohamed Roomy Mohamed Hassan: CHANGED: Was 'Pending with RSG/FFC' → 'DVO RR Issued'
Note on N67: Mohamed Roomy Mohamed Hassan: RSG Employer Assessment accepted amount for R06-HW2C05-TRS-VOR-CM-0043 FOH Panic Bar Hardware. Contractor proposal: SAR 8,287.40. Difference: -SAR 1,592.60 (Electromagnetic lock already included in Card Reader item per RSG).
Note on O71: Mohamed Roomy Mohamed Hassan: Signed and sent DVO to RSG
Note on O81: Mohamed Roomy Mohamed Hassan: Mohamed Roomy Mohamed Hassan: Signed and sent DVO to RSG

## Sheet1
Pending with FFC | 9 | 0 | 0
Pending with RSG | 22 | 2991535.5681 | 9676283.7331
Pending with RSG/FFC | 4 | 6684748.165
Approved , Pending DVO | 18 | -23074.7487
DVO RR Issued | 8 | -362299.9724
DVO Issued | 22 | 15744722.6074
Total Submitted VO | 74 | 25035631.6194

## Sheet2 (hidden)
PAYMENT REGISTER-HW2C05
PROJECT DETAILS
Project: | R06-HW2C05-5020
Contractor: | First Fix
Currancy SAR
Summary of IPA's (without VAT) |  |  |  | `
Original Contract Value | 217501556.1159
Revised Contract Value | 232708408.6612
PAYMENT STATUS |  |  |  |  | .
| Gross amount |  | Net amount
Under Review | 12000000 | 6% | 8771580
Submitted on ACONEX | 6418102.3521 | 7.737% | 4691408.1858
Approved via Acconex | 18005054.06 | 2.758% | 13161064.341
Received | 148847011.4366 | 63.96% | 114032222.1404
Total Work Done | 173270167.8487 | 74.46% | 131884694.6672
Balance Work Done | 59438240.8125 | 25.54% | 54239999.4954
SUMMARY OF ADVANCE PAYMENT RECOVERY IPA
Advance Payment | 65250466.8332 | 32.09%
Deducted till Date | 51054339.1184 | 78.24%
Balance | 14196127.7148 | 21.76%
SUMMARY OF RETENTION IPA
Total Retention | 10875077.8058 | 5%
Deducted till Date | 8663508.3727 | 79.66%
Balance | 2211569.4331 | 20.34%
VO STATUS
| Pending with FFC | 1 | 45000
| Pending with RSG | 27 | 11680021.1571
| Pending with RSG/FFC | 9 | 4136961.37
| Approved & Awaiting for the DVO to be issued | 3 | -113950.17
| DVO RR Issued | 10 | 15320802.7153
| Total Submitted VO | 49 | 31023835.0724

## VO LOG (New) (hidden)
VARIATION ORDER LOG
HW2 MEP ¦ Pay Reg & VO Tracking | [12 empty] | 2026-07-29
TOTAL VOs |  | DVO ISSUED |  | APPROVED |  | PENDING RSG/FFC |  | PENDING RSG |  | PENDING FFC |  | APPROVED VALUE |  |  | Status | Count
#REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  |  | DVO Issued | #REF!
Submitted |  | Closed Out |  | Awaiting DVO |  | Joint Review |  | Under Assessment |  | Action Required |  | SAR Total |  |  | Approved | #REF!
[15 empty] | Pending RSG/FFC | #REF!
# | SUBJECT | TYPE | SUBMITTED | COST PROPOSAL | RSG ASSESSMENT | FINAL APPROVED | STATUS | VOR REF | DVO REF | SUBMISSION REF | FFC REMARKS | LIVE ACTION | RSG REMARKS | ASSIGNED | Pending RSG | #REF!
| ✅ DVO RR ISSUED |  |  |  |  | 19 items | [8 empty] | Pending FFC | #REF!
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 🔵 APPROVED — AWAITING DVO |  |  |  |  | 6 items
20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 🟡 PENDING WITH RSG/FFC |  |  |  |  | 10 items
26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
32 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
33 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
34 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
35 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| PENDING WITH RSG |  |  |  |  | 28 items
36 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
37 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
38 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
39 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
40 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
41 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
42 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
43 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
44 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
45 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
46 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
47 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
48 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
49 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
50 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
51 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
52 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
53 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
54 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
55 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
56 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
57 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
58 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
59 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
60 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
61 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
62 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
63 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| PENDING WITH FFC |  |  |  |  | 6 items
64 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
65 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
66 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
67 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
68 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
69 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| NOT ELIGIBLE |  |  |  |  | 1 items
70 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
TOTAL |  |  |  | #REF! |  | #REF!